## Sheet1
Week | <component> | Estimated Hours of Effort | Actual Hours of Effort
2021-05-31 | Develop spreadsheet of tasks | 1 | 0.5
2021-05-31 | Set of Trello Board | 1 | 2
2021-05-31 | Set up Azure Cloud Shell | 1 | 0.67
2021-05-31 | Create Project Scaffolding | 1 | 0.083333
2021-05-31 | Create Makefile | 1 | 0.083333
2021-05-31 | Create requirements.txt | 1 | 0.083333
2021-05-31 | Create Python Virtual Environment | 1 | 0.083333
2021-05-31 | Create script file | 1 | 0.083333
2021-05-31 | Create test file | 1 | 0.083333
2021-05-31 | Conduct Local Test | 1 | 0.5
2021-05-31 | Artifact: Take a screenshot showing passing tests that are displayed by running make all during Local Test | 1 | 0.33
2021-05-31 | Configure GitHub Actions | 1 | 0.083333
2021-05-31 | Replace yaml code | 1 | 0.083333
2021-05-31 | Verify Remote Tests pass | 1 | 0.083333
2021-05-31 | Artifact: Take a screenshot passing GitHub Actions build and put into README.md | 1 | 0.083333
2021-05-31 | Get Flask starter code and add it to your project | 1 | 0.083333
2021-05-31 | Replace scaffolding code with Flask Machine Learning code | 1 | 0.33
2021-05-31 | Authorize Azure App Service | 1 | 0.5
2021-05-31 | Enable continuous deployment with Azure Pipelines | 1 | 2
2021-05-31 | Check-in Azure Pipelines YAML-based config file into Github | 1 | 0.5
2021-05-31 | Enable Github + Azure Pipelines | 1 | 0.33
2021-05-31 | Deploy project in Azure Pipelines | 1 | 0.5
2021-05-31 | Verify predition with starter code file | 1 | 0.083333
2021-06-07 | Complete Todo's in template README.md file | 10 | 15
2021-06-07 | Put README in root dir of your Github repository | 1 | 0.5
2021-06-14 | Get locust testing working with locustfile.py | 10 | 12
2021-06-21 | Create video demo | 15 | 15
|  | 59 | 51.66