## CICD Pipeline
Week | <component> | Estimated Hours of Effort | Actual Hours of Effort
2021-05-31 | Develop spreadsheet of tasks | 1 | 0.5
2021-05-31 | Set of Trello Board | 1 | 2
2021-05-31 | Set up Azure Cloud Shell | 1 | 0.67
2021-05-31 | Create Project Scaffolding | 1 | 0.083333
2021-05-31 | Create Makefile | 1 | 0.083333
2021-05-31 | Create requirements.txt | 1 | 0.083333
2021-05-31 | Create Python Virtual Environment | 1 | 0.083333
2021-05-31 | Create script file | 1 | 0.083333
2021-05-31 | Create test file | 1 | 0.083333
2021-05-31 | Conduct Local Test | 1 | 0.5
2021-05-31 | Artifact: Take a screenshot showing passing tests that are displayed by running make all during Local Test | 1 | 0.33
2021-05-31 | Configure GitHub Actions | 1 | 0.083333
2021-05-31 | Replace yaml code | 1 | 0.083333
2021-05-31 | Verify Remote Tests pass | 1 | 0.083333
2021-05-31 | Artifact: Take a screenshot passing GitHub Actions build and put into README.md | 1 | 0.083333
2021-05-31 | Get Flask starter code and add it to your project | 1 | 0.083333
2021-05-31 | Replace scaffolding code with Flask Machine Learning code | 1 | 0.33
2021-05-31 | Authorize Azure App Service | 1 | 0.5
2021-05-31 | Enable continuous deployment with Azure Pipelines | 1 | 2
2021-05-31 | Check-in Azure Pipelines YAML-based config file into Github | 1 | 0.5
2021-05-31 | Enable Github + Azure Pipelines | 1 | 0.33
2021-05-31 | Deploy project in Azure Pipelines | 1 | 0.5
2021-05-31 | Verify predition with starter code file | 1 | 0.083333
2021-06-07 | Complete Todo's in template README.md file | 10 | 15
2021-06-07 | Put README in root dir of your Github repository | 1 | 0.5
2021-06-14 | Get locust testing working with locustfile.py | 10 | 12
2021-06-21 | Create video demo | 15 | 15
|  | 59 | 51.66

## 3Q21
Week | <component> | Estimated Hours of Effort
2021-06-28 | Add testing and collect coverage metrics | 3
2021-07-05 | Build an image and push to Azure Container Registry | 2
2021-07-12 | Set up Kubernetes environment | 3
2021-07-19 | Automate the Kubernetes environment setup with Terraform | 4
2021-07-26 | Deploy the application on Kubernetes | 1
2021-08-02 | Build automation to deploy the application to Kubernetes | 1
2021-08-09 | Introduce auto-scaling to enable Kubernetes to grow the number of instances based on load | 2
2021-08-16 | Drive and test auto-scaling through locust; see number of instances test; need LB in front | 3
2021-08-23 | Document experiments in auto-scaling | 2
2021-08-30 | Update README and code to incorporate Kubernetes setup and deployment | 4
2021-09-06 | Set up wiki to answer additional questions | 3
2021-09-13 | Test new application and predictions; make bug fixes | 2
2021-09-20 | Document test results | 3
33
Overall Objectives for 3Q21
Add additional functions to the Azure Pipeline

## 4Q21
Week | <component> | Estimated Hours of Effort
2021-09-27 | Set up Jupyter notebook environment | 6
2021-10-04 | Build initial notebook for the model | 2
2021-10-11 | Experiment with different models | 10
2021-10-18 | Evaluate models based on accuracy, recall, precision, F1 score, and ROC curve | 15
2021-10-25 | Save the best model using joblib or pickle | 2
2021-11-01 | Insert model in a flask application | 1
2021-11-08 | Build a container for the application and model | 1
2021-11-15 | Deploy the containerized application | 1
2021-11-22 | Set up an A/B test for the new application vs. existing application | 3
2021-11-29 | Document results of the experiment | 10
2021-12-06 | If new application predicts better than the existing application, replace existing | 1
2021-12-13 | Document model approach and results | 10
2021-12-20 | Update readme to include creation, testing, and deployment of a new model | 15
2021-12-27 | Deploy new readme | 1
78
Overall Objectives for 4Q21
Link in a Jupyter notebook for the Boston Housing ML model as another pipeline, deploying the joblib or a pickle file to Github and then doing the application build and deploy.